## GIMP 2.8
	This document contains a GIMP development schedule. / This sheet contains a list of tasks that needs to be done before GIMP 2.8 is ready for release. An estimate of the time to complete each task, in 8-hour work days, is also given. Based on this data an estimated date when we will have a GIMP 2.8 release candidate ready is calculated. Each column of estimates represents a snapshot at a given point in time. '0' means 'complete' and no entry means 'de-scoped'. The formula includes a “days worked per week”-factor that specifies how many 8-hour work days that the GIMP community together produces per week. There is also a sheet where things planned for GIMP 2.10/3.0 is put.
	Days worked per week	3	3	3	3	3
	GIMP 2.8 Release Candidate is ready:	2011-03-15	2010-12-11	2010-12-17	2010-11-21	2010-12-29
	Date of snapshot	2010-01-15	2010-01-23	2010-02-16	2010-03-07	2010-06-22

	Single-window mode
	Cleanup image window desctruction to get rid of valgrind warning	1	1	1	1	1
	Implement image parade	10	10	10	10	10
	Support dnd between dockables, on GtkPaned handles	3	3	3	3	2
	Make only dockables be droppable on drag handlers		1	1	1	1
	Refactor dock window/dialog/dockable factory/construction mechanism	3	0	0	0	0
	Add "toolbox" and "dock" as dialog factory entries	2	0	0	0	0
	Merge global_toolbox_factory with global_dock_window_factory	2	0	0	0	0
	Fix toolbox multi-column dnd	2	0	0	0	0
	Make Tab work in swm	4	4	4	0	0

	Brush dynamics
	Come up with a UI spec for the dialog	4	4	4	4	2
	Get hold of icons	5	5	5	5	1
	Fix random crash in history buffer	3	3	3	0	0
	Wire curves to something on screen, connect to mixing	3.5	3.5	3.5	0	0
	Put curves in the dynamics file	1	1	1	0	0

	Miscellaneous
	Write release notes	3	3	3	3	3
	Bring release from git to website news					3

	Bugs
622311	Get rid of status bar grip window in single-window mode			2	2	1
622096	Add PDB API to manipulate and access layer groups					4
622073	Flicker in drawing tools					4
620674	Adding support for multi-colored text layer					2
612931	Moving individual layer in layer group not possible with Move Tool					3
608961	Make GIMP color management behavior reasonable					3
603848	Single-window mode is not properly session managed yet	5	5	5	5	5
600554	Implement layer group transforms	1	1	1	1	3
599065	PNG output: omit unwanted chunks (sRGB)	0.5	0.5	0.5	0.5	0.5
598320	Unrelated fields saved in presets	1	1	1	1	1
597117	impossible to drop a group as a sibling inside a group	1	1	1	1	1
596410	gimp-image-get-filename returns NULL for imported files	0.5	0.5	0.5	0.5	1
592611	Support tagging of multiple resources simultaneously	3	3	3	3	3
589371	Improve default set of resources	2	2	2	2	2
589010	Don't select item in GimpContainerTreeView when clicking with modifier keys	2	2	2	2	2
581338	Layer size does not change using the pdb 'gimp-text-layer-resize'	1	1	1	1	1
574018	Add a manifest to executables					1
573542	blur plugin: bug in the first line	0.5	0.5	0.5	0.5	0.5
572997	gih description alter when re-saving	0.5	0.5	0.5	0.5	0.5
565046	Point snapping to guides does not work outside the canvas	2	2	2	2	2
553390	downscaling quality again	7	7	7	7	2
382688	Export as a PDF file	1	1	1	1	1
367388	Small/percentage adjustment actions for tool-value and tip-sizes	1	1	1	1	1
309196	editing an image while a save is in progress can cause corruption	3	3	3	3	3
119874	Organize brushes into categories	3	3	3	3	1
61499	easy way to view/edit image metadata (author, copyright, image title, etc.)	5	5	5	5	5
51112	clipping groups or masking groups (like in Photoshop files)	3	3	3	3	3
50638	Use lookup table for tablet pressure	2	2	2	2	2

	COMPLETED :)

	On-canvas text editing
	Final polishing	3	3	3	0	0

	Bugs
604175	gimp_vectors_import() is O(n**2) in gimp_list_uniquefy_name(), for some data	1	1	0	0	0
598344	Better new/old color management in dialog (patch included!)	0.5	0	0	0	0
119240	Dynamic Brush stroke panel and/or Dynamic path stroke	5	5	5	0	0
346881	Remove redundant title of tab and move menu button up	5	5	4	4	0
554927	The window title in tools windows uses a non localizable comma	0.5	0.5	0.5	0	0
574149	Can't get name/filename of files loaded from URI	0.5	0	0	0	0
568445	Closing the Toolbox causes the program to close	0.5	0.5	0.5	0	0
597368	Gimp is stealin my pixels	1	1	0	0	0
596427	Can't export to animated GIF	0.5	0.5	0	0	0
610587	Zooming with zoom tool pans away from the cursor				2	0
595537	Text tool crashes GIMP	1	1	1	1	0
499443	Invalid call to apply function makes script-fu crash	0.5	0.5	0.5	0.5	0

	POSTPONED :(

	Bugs
595708	WM_WINDOW_ROLE should be unique	0.5	0.5
592173	Get rid of brush scaling and introduce a master diameter instead	5
583778	change script-fu-server to return the output of executed commands	1	1	1
575006	Add preferences for snapping	1	1
574418	Saving a selection to a channel should not change the active drawable	1
565973	Changing the image comment does not mark the image as modified	0.5	0.5
565268	unlocalizable string in script-fu-carve-it	0.5	0.5
561576	Modifier key to create new layer from floating selection	1	1	1	1
556884	More messages marked for translation	0.5	0.5
539724	brush pipe selection for smudge is incorrect	1	1	1	1
525705	skip thumbnailing entirely on files with insufficient read permissions	2
508183	Crop tool to once again display selection aspect ratio along with size (in status?)	2
507257	Add a "Save Keyboard Shortcuts Now" button to the Configure Keyboard Shortcuts dialog	1	1	1	1
506730	Wrap GIMP brushes as python objects	1
479875	performance problem drawing a complex selection	1
459518	Channel preview becomes black when the channel is deselected	3
387779	Transform tools could make better use of cursor keys	3
358141	Add session management for plug-in windows	4
349224	Creative Commons licenses integration	2
347127	flattened image differs from multilayered image	3	3
314379	add a libart version of gimp-edit-stroke to PDB	2
169616	Text along a path	1
155733	need to check return values of gimp_drawable_mask_bounds()	3	3	3	3
120829	Save presets in plug-ins.	3
56443	Add support for EXIF or TIFF/EP data (in JPEG, TIFF and PNG formats)	5
128068	Brush Spacing options should be accessible from the tool options	3	3	3	3
582755	Addition of golden spiral to rectangle tool guides	0.5	0.5	0.5	0.5
576910	Change Language setting	1	1	1	1
326869	last "save a copy" location permanently stored	3	3	3	3

	Merge SIOX improvements (didn't even compile for me...)
	Do it and clean up	5	5	5	5

	Merge vector layer code
	Make undo work	2	2	2	2
	Clean up the UI	3	3	3	3
	Merge the code	1	1	1	1
	Get fundamental unit testing in place	3	3	3	3
	Extend XCF test cases with vector layers	2	2	2	2

## GIMP 2.10slash3.0
We save the work of splitting up features into smaller tasks and estimating the work involved by putting things postponed from GIMP 2.8 into this sheet.
Days worked per week	3
Total weeks of work:	42.33

Cairo drawing on canvas
Come up with infrastructure	5
Port tools to use cairo for drawing	30

Unified transform tool
Implement	20

Free transform tool
Do it	30

Bugs
486902, Remove the "add/remove alpha channel" option for layers	15
65197, New tool please: Shapes	20
320447, fast switching between "color managed display" and "softproof"	4
512022, Live histogram for the whole image (projection)	3