## GIMP 2.8
This document contains a GIMP development schedule. / This sheet contains a list of tasks that needs to be done before GIMP 2.8 is ready for release. An estimate of the time to complete each task, in 8-hour work days, is also given. Based on this data an estimated date when we will have a GIMP 2.8 release candidate ready is calculated. Each column of estimates represents a snapshot at a given point in time. '0' means 'complete' and no entry means 'de-scoped'. The formula includes a “days worked per week”-factor that specifies how many 8-hour work days that the GIMP community together produces per week. There is also a sheet where things planned for GIMP 2.10/3.0 is put.
Days worked per week	3	3	3
GIMP 2.8 Release Candidate is ready:	2011-04-01	2010-12-27	2010-12-26
Date of snapshot	2010-01-15	2010-01-23	2010-02-16

Merge vector layer code
Make undo work	2	2	2
Clean up the UI	3	3	3
Merge the code	1	1	1
Get fundamental unit testing in place	3	3	3
Extend XCF test cases with vector layers	2	2	2

On-canvas text editing
Final polishing	3	3	3

Resource tagging
Support tagging multiple resources simultaneously	3	3	3

Default resources
Improve default set as outlined in bug 589371	2	2	2
Assign default tags to default resources	2	2	2

Brush dynamics
Wire curves to something on screen, connect to mixing	3.5	3.5	3.5
Come up with a UI spec for the dialog	4	4	4
Put curves in the dynamics file	1	1	1
Get hold of icons	5	5	5
Fix random crash in history buffer	3	3	3

Merge SIOX improvements (didn't even compile for me...)
Do it and clean up	5	5	5

Layer groups
Add test cases for layer groups	2	2	2
Double-check 2.6 backward and forward compatibility	3	3	0
600554, Either implement or disable layer group transforms	1	1	1
597117, impossible to drop a group as a sibling inside a group	1	1	1

Single-window mode
Refactor dock window/dialog/dockable factory/construction mechanism	3	0	0
Add "toolbox" and "dock" as dialog factory entries	2	0	0
Merge global_toolbox_factory with global_dock_window_factory	2	0	0
Fix toolbox multi-column dnd	2	0	0
Cleanup image window desctruction to get rid of valgrind warning	1	1	1
Implement swm and mwm session management	5	5	5
Implement image parade	10	10	10
Support dnd between dockables, on GtkPaned handles	3	3	3
Make only dockables be droppable on drag handlers		1	1
Make Tab work in swm	4	4	4
Make alt-switching of image tabs work			0,5
Move window resize handle to a proper place			2

Miscellaneous
Write release notes	3	3	3

Bugs
604175, gimp_vectors_import() is O(n**2) in gimp_list_uniquefy_name(), for some data	1	1	0
599065, PNG output: omit unwanted chunks (sRGB)	0.5	0.5	0.5
598344, Better new/old color management in dialog (patch included!)	0.5	0	0
598320, Unrelated fields saved in presets	1	1	1
597368, Gimp is stealin my pixels	1	1	0
596427, Can't export to animated GIF	0.5	0.5	0
596410, gimp-image-get-filename returns NULL for imported files	0.5	0.5	0.5
595708, WM_WINDOW_ROLE should be unique	0.5	0.5
595537, Text tool crashes GIMP	1	1	1
592173, Get rid of brush scaling and introduce a master diameter instead	5
589010, Don't select item in GimpContainerTreeView when clicking with modifier keys	2	2	2
583778, change script-fu-server to return the output of executed commands	1	1	1
582755, Addition of golden spiral to rectangle tool guides	0.5	0.5	0.5
581338, Layer size does not change using the pdb 'gimp-text-layer-resize'	1	1	1
576910, Change Language setting	1	1	1
575006, Add preferences for snapping	1	1
574418, Saving a selection to a channel should not change the active drawable	1
574149, Can't get name/filename of files loaded from URI	0.5	0	0
573542, blur plugin: bug in the first line	0.5	0.5	0.5
572997, gih description alter when re-saving	0.5	0.5	0.5
568445, Closing the Toolbox causes the program to close	0.5	0.5	0.5
565973, Changing the image comment does not mark the image as modified	0.5	0.5
565268, unlocalizable string in script-fu-carve-it	0.5	0.5
565046, Point snapping to guides does not work outside the canvas	2	2	2
561576, Modifier key to create new layer from floating selection	1	1	1
556884, More messages marked for translation	0.5	0.5
554927, The window title in tools windows uses a non localizable comma	0.5	0.5	0.5
553390, downscaling quality again	7	7	7
539724, brush pipe selection for smudge is incorrect	1	1	1
525705, skip thumbnailing entirely on files with insufficient read permissions	2
508183, Crop tool to once again display selection aspect ratio along with size (in status?)	2
507257, Add a "Save Keyboard Shortcuts Now" button to the Configure Keyboard Shortcuts dialog	1	1	1
506730, Wrap GIMP brushes as python objects	1
499443, Invalid call to apply function makes script-fu crash	0.5	0.5	0.5
479875, performance problem drawing a complex selection	1
459518, Channel preview becomes black when the channel is deselected	3
387779, Transform tools could make better use of cursor keys	3
382688, Export as a PDF file	1	1	1
367388, Small/percentage adjustment actions for tool-value and tip-sizes	1	1	1
358141, Add session management for plug-in windows	4
349224, Creative Commons licenses integration	2
347127, flattened image differs from multilayered image	3	3
346881, Remove redundant title of tab and move menu button up	5	5	4
326869, last "save a copy" location permanently stored	3	3	3
314379, add a libart version of gimp-edit-stroke to PDB	2
309196, editing an image while a save is in progress can cause corruption	3	3	3
169616, Text along a path	1
155733, need to check return values of gimp_drawable_mask_bounds()	3	3	3
128068, Brush Spacing options should be accessible from the tool options	3	3	3
120829, Save presets in plug-ins.	3
119874, Organize brushes into categories	3	3	3
119240, Dynamic Brush stroke panel and/or Dynamic path stroke	5	5	5
61499, easy way to view/edit image metadata (author, copyright, image title, etc.)	5	5	5
56443, Add support for EXIF or TIFF/EP data (in JPEG, TIFF and PNG formats)	5
51112, clipping groups or masking groups (like in Photoshop files)	3	3	3
50638, Use lookup table for tablet pressure	2	2	2

## GIMP 2.10slash3.0
We save the work of splitting up features into smaller tasks and estimating the work involved by putting things postponed from GIMP 2.8 into this sheet.
Days worked per week	3
Total weeks of work:	42.33

Cairo drawing on canvas
Come up with infrastructure	5
Port tools to use cairo for drawing	30

Unified transform tool
Implement	20

Free transform tool
Do it	30

Bugs
486902, Remove the "add/remove alpha channel" option for layers	15
65197, New tool please: Shapes	20
320447, fast switching between "color managed display" and "softproof"	4
512022, Live histogram for the whole image (projection)	3